## Sheet1
Stand-up questions | #1 | #2 | #3 | #4 | #5 | #6 | #7 | #8
| 02/11/2025-02/25/2025 | 02/26/2025-03/11/2025 | 03/12/2025-03/25/2025 | 03/26/2025-04/08/2025 | 04/09/2025-04/15/2025 | 04/16/2025-04/22/2025 | 04/23/2025-04/29/2025 | 04/30/2025-05/12/2025
Sanjushree Golla
What tasks did I work on / complete? | Project Setup, Repo Initializing, Setting project structure | Built backend for login and registration forms and roting is done for those, APIs are built | Completed booking API, added confirmation email functionality | Created restaurant listing frontend, added filters and pagination | Hooked up register/login pages to backend | Refactored code for reusability and responsiveness | Prepared project for deployment (staging files been generated) | Final bug fixes and feature toggles
What am I planning to work on next? | Design login/register forms and route logic | Implement booking API and the manger data analyzing for the restaunt manager | Integrate cancel booking API | Setup edit/delete action handlers | Add error messages and success feedback | Final code polish and clean-up | Test app end-to-end on staging | Present demo
What tasks are blocked waiting on another team member? | NA | NA | NA | Waiting for delete API test |  | NA | NA | N/A
Chanukya Vejandla
What tasks did I work on / complete? | Database design model, Setup for the tables in the mysql, setup db connections | Developed routing for the tables selections, tables managing during customer reservation | Connected UI to search + booking APIs, performed basic testing meanwhile, Populated mock data for restaurants | Secured route access for user roles, wrote SQL triggers for reviews | Implemented session management logic | Added toast alerts and consistent navigation | Verified schema compliance and app boot | Provided DB schema ER diagram and docs and done the cloud deployement on EC2 and S3 on AWS
What am I planning to work on next? | Set up protected routes and start role-based access | Connect UI to APIs | Improve error handling and secure access for user roles | Connect DB Hooks with backend endpoints | Write tests for middleware protection | Polish loading states and DB consistency check | Create final SQL export and notes
What tasks are blocked waiting on another team member? | NA | Waiting for Sanju’s booking API to be ready | N/A | N/A | NA | NA | N/A | NA
Harsha Vardhan Badithaboina
What tasks did I work on / complete? | Designed wireframes for the customer page, login page and other views | UI for the login,register, customer | Booking interface is done | Improved the UI dashboards for the manager and customer | Finalized data validations and constraints in schema | Final frontend polish and clean-up done | Supported integration testing | Submit GitHub + documentation
What am I planning to work on next? | Implement the React frontend part for the customer and manager roles | Create booking interface | unit testing and improving the UI features | Help with data adjustments | Add automatic role assignment on signup | Run and perform tests | Prepare presentation assets | Review grading checklist
What tasks are blocked waiting on another team member? | NA | NA | NA | NA | NA | NA | NA | N/A
Jayanth Yarlagadda
What tasks did I work on / complete? | Designed admin dashboard wireframes, created layout mock | Built basic admin and manager dashboard UI | Built user management tables in admin panel | Added restaurant table views for admin | Created admin stats summary cards | Implemented user search and filters | Final UI refinements and bug fixing | Recorded admin-side demo
What am I planning to work on next? | Build base admin UI and connect routing | Design and build the analytics dashboard | Add user delete and edit functions | Integrate filters and batch delete | Add Chart Integration | Add review management tab | Work on README or the documentation for the project | Finalize README and deployment note
What tasks are blocked waiting on another team member? | NA | NA | Waiting on API for user role validation | NA | Waiting on backend data for reviews count | Waiting for the data to include test reviews | NA | NA