## Table 1
TEAM : CODE CATALYSTS
Weeks | Task | Story Points | Task Owner | Working Hours | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7
#1 | Planning + Tech Stack + Initialization | 5 | Sanju,Chanukya,Harsha,Jayanth | 7 | 2 | 1 | 0 | 0 | 2 | 1 | 1
| Initialized the react app built base layout. | 5 | Harsha | 6 | 1 | 2 | 0 | 0 | 2 | 1 | 0
| Created project structure, Created basic auth middleware | 15 | Sanju | 5 | 1 | 1 | 1 | 0 | 2 | 0 | 0
| Worked on schema diagrams, defined entities and relationships. and Designed UI wireframes and initial landing page components. | 10 | Chanukya, Jayanth | 6 | 2 | 1 | 0 | 1 | 0 | 1 | 1
#2 | Built search API, input validation | 10 | Sanju | 7 | 0 | 1 | 0 | 3 | 1 | 1 | 1
| UI for the login, register, customer and manager pages. | 5 | Harsha | 5 | 1 | 1 | 1 | 1 | 0 | 1 | 0
| Created mock data for restaurants, users, and roles. | 13 | Chanukya | 4 | 0 | 1 | 0 | 0 | 0 | 2 | 1
| Built admin dashboard skeleton, placeholder routes. | 5 | Jayanth | 5 | 2 | 1 | 0 | 1 | 0 | 0 | 2
#3 | Completed booking API, added confirmation mail logic. | 8 | Sanju | 6 | 2 | 0 | 1 | 1 | 0 | 2 | 0
| Developed dynamic frontend search + booking pages. | 8 | Harsha | 4 | 1 | 0 | 2 | 1 | 1 | 0 | 0
| Finished test cases for DB operations and auth middleware. | 13 | Chanukya | 7 | 1 | 2 | 0 | 1 | 0 | 1 | 1
| Created styled components and custom form layouts. | 5 | Jayanth | 5 | 1 | 0 | 2 | 1 | 1 | 0 | 0
#4 | Created restaurant listing frontend, added filters by category. | 8 | Harsha | 4 | 0 | 2 | 0 | 1 | 1 | 0 | 0
| Secured routes based on user roles and JWT verification. | 8 | Sanju | 6 | 0 | 1 | 0 | 0 | 0 | 2 | 3
| Finalized DB triggers for auto updates on delete/edit. | 8 | Chanukya | 5 | 2 | 0 | 0 | 0 | 1 | 1 | 1
| Improved UI for loader, error display, and responsiveness. | 8 | Jayanth | 5 | 0 | 2 | 0 | 1 | 1 | 0 | 1
#5 | Hooked up login/register pages to backend API and Implemented session persistence with cookies/localStorage | 8 | Sanju | 6 | 3 | 0 | 0 | 1 | 1 | 0 | 1
| Built the ui pages for the reviews, restaurant listings | 5 | Harsha | 3 | 2 | 0 | 0 | 1 | 1 | 1 | 0
| Wrote unit tests for all DB models and service logic. | 10 | Chanukya | 5 | 1 | 2 | 0 | 0 | 1 | 0 | 1
| Styled and adjusted spacing/layout issues. | 8 | Jayanth | 6 | 0 | 1 | 1 | 1 | 0 | 2 | 1
#6 | Added alerts for login/logout/booking success/failure. | 18 | Sanju | 4 | 1 | 3 | 0 | 0 | 1 | 0 | 0
| Refactored reusable components for form, header, footer. | 5 | Harsha | 5 | 1 | 0 | 1 | 4 | 0 | 0 | 0
| Validated all input data and resolved console errors | 8 | Chanukya | 4 | 0 | 1 | 0 | 1 | 1 | 0 | 1
| Fixed broken links, added page-level metadata. | 5 | Jayanth | 6 | 1 | 0 | 0 | 1 | 2 | 0 | 2
#7 | Configured deployment with AWS + tested endpoint links. | 10 | Chanukya | 5 | 0 | 0 | 0 | 0 | 3 | 1 | 1
| Integrated project with staging files+ tested search/booking. | 5 | Sanju | 6 | 1 | 0 | 1 | 2 | 1 | 1 | 0
| Supported E2E testing and bug patching during review. | 10 | Harsha | 5 | 0 | 1 | 1 | 1 | 1 | 0 | 1
| Final polish on UI animations, shadows, and transitions. | 3 | Jayanth | 4 | 1 | 1 | 0 | 1 | 2 | 0 | 0
#8 | Final bug fixes, feature toggles and deployed backend in EC2 | 5 | Chanukya | 4 | 1 | 2 | 0 | 0 | 0 | 1 | 0
| Created the ui walkthrough. | 18 | Harsha | 5 | 1 | 0 | 1 | 0 | 2 | 0 | 1
| Submitted GitHub repo, added README, usage. | 8 | Sanju | 6 | 2 | 2 | 0 | 2 | 0 | 0 | 0
| Final document and readme polishing | 5 | Jayanth | 4 | 1 | 1 | 1 | 0 | 0 | 1 | 0
Total |  | 210 |  | 180